## Schedule
Asset | Reviewer | Completion Week | Details Provided | Status
Core Frameworks | Sai |  | Yes
Kreator | Trividha | 2023-04-07 | Yes | In Progress
Child Support | Sai |  | Yes
Child Welfare | Trisha | 2023-04-21 | Yes | Complete
IDS | Trisha | 2023-04-07 | Yes | Complete
Grants Mgmt | Trisha | 2023-04-14 | Yes | Complete
LTSS | Sai |  | Yes
DMV DL | Trividha | 2023-04-14 | Yes | Complete
DMV NMVTIS | Trividha | 2023-04-21 | Yes | Complete

## Bronze - DMV DL
Test Scripts & Scenarios
Category | Metrics | Results | Recommendations | Score
Test Scripts | Atomic | Pass | Scoped test scrips were logically broken in almost all US's that were reviewed.
| Clear objective | Fail | Giving few examples to help team understand what needs to be corrected: 1. DL: Agency Check Response data specific to a persona: SCDVR-4864 & File Upload Allowable types & File Clearing: SCDVR-5000 a. Test Script Format: i. Accurate Test Title It is observed that test Title/Description is copy paste from US and doesn't explain what is the purpose of the test script.
| Prerequisites, Personas & Org/Portal details mentioned | Partially Met | Giving few examples to help team understand what needs to be corrected: 1. Retention of uploaded documents: SCDVR-4652 & WP Print receipt: SCDVR-4976 a. Test Script Format: i. Pre-requisites should be associated to each script & should not be included as part of wrapper test script description 2. Data Update Scripts: SCDVR-4842 & File Upload Allowable types & File Clearing: SCDVR-5000 a. Test Script Format: i. Pre-requisites are not captured accurately 3. DL: Agency Check Response data specific to a persona: SCDVR-4864 a. Test Script Format: i. Pre-requisite should link to the test step when referred. Inorder to perform replace/renew flow the corresponding pre-requisite to have a valid credential is missing
| Detailed & concise documentation | Partially Met | 1. Data Update Scripts: SCDVR-4842 a. Test steps need to be more meticulous i. Information that needs to be deleted should be explicitly called out & verified ii. Demographics information that needs to be retained should be explicitly called out & verified
| Traceability to requirements | Pass | Scripts are atomic & can be tracked back to the requirements mentioned in US AC.
| Coverage: +ve/-ve scenarios, boundary value testing | Partially Met | Giving few examples to help team understand what needs to be corrected: 1. Retention of uploaded documents: SCDVR-4652 a. Exhaustive test coverage is missing i. AC# 2 is not validated in test scripts ii. Validate the format types as well for document retention iii. Document retention should be validated after multiple back & forth instead of just validating it by coming back one screen 2. WP Print receipt: SCDVR-4976 b. Exhaustive test coverage is missing i. Format of the print receipt is not validated ii. Details should be explicitly called out in terms to what will show up on the receipt. iii. Ability to print & save is not included 3. File Upload Allowable types & File Clearing: SCDVR-5000 a. Exhaustive test coverage is missing i. 1 file type (bmp) was not test ii. Non-allowable file types are not validated iii. File size is not validated [no mention of it being out of US scope] iv. Flow not validated for renew & replace
| Format (inline w/ GC standards) | Pass | Test script format doesn’t align with GC as DMV uses Jira instead of Tracker. Also, current format looks good.
| Scripts reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Pass | Reviewed by Aparna Mahanta/Trisha Chakraborty
Regression Suite | Updated till Sprint current-1 | Pass | Yes, Confirmed by Asset Lead.
| Reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Pass | Reviewed by Aparna Mahanta/Trisha Chakraborty
| Format Recommendation: Script test cases module wise instead of maintaining 1 big e2e script | Fail | a. Test script format: i. Scripts are like e2e in nature instead of covering regression scenarios in detail. ii. Recommendation is to split them into multiple scripts 1) E.g.: New Issuance: a) Submitting a request from CP b) Review from WP when it requires worker intervention: Approved flow c) Review from WP when it requires worker intervention: Rejected flow d) Auto approval of application e) Verification in CP 2) Replace a) Flow wherein there is change in demographics/address, etc. iii. Some steps should be atomic as there is more than 1 action being performed & validated and having multiple actions in a single step may confuse the audience. iv. Always separate out layout validation from business logic validation. v. Expected results needs to be specific & not generic. vi. Be specific in pre-requisites 1) Community user should be registered How would a CP user know Person Account eligible for Replacement/Renewal
| Coverage: All modules w/ +ve/-ve, functional, UI, integration, etc. scenarios | Fail | a. Exhaustive Coverage: i. Only happy path is covered. Its instructed in the script the option to select so as to complete the happy flow only. 1) Check around fee calculation is missing 2) Melissa address validation 3) Credentials displayed as per the age criteria, etc. Check on renewal criteria: eligible vs ineligible timeframe
Execution
Scope Testing | Test scripts executed for each passed story | Pass | They're attached as attachments & not executed as per Jira.
| Scope testing inline with test scripts | Pass | What is documented in test scripts is validated. Refer recommendation to make test scripts more exhaustive.
| Test data and/or screenshots captured for each user story/ticket | Partially Met | Only one US observed from the subset reviewed where test documentation was not attached. 1. Retention of uploaded documents: SCDVR-4652 Test documentation (test data/screenshots/videos) not attached Note: I would've ignore this as one-off incident but the US was tested by Test lead s0 no exceptions!
| Detailed documentation of tickets - Problem Statement - Steps of Replicate - Actual Result - Expected Result - Test Data - Screenshots - Business Impact tagged as per severity - Key information populated on the ticket (Logged By, Tester, US, Sprint, Project, Status) | Partially Met | 1. Bug Observation a. Steps to replicate should be clearly stated in points if they are more than 2 instead of writing a paragraph or a statement b. Mention the issue in detail instead of stating a generic statement e.g. "Transaction Receipt not populating all data." c. No test data/scenario to trace the bug to test script when bug is logged/closed
| Outcomes reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Pass | Reviewed by Aparna Mahanta/Trisha Chakraborty
Regression Testing | Regression suite executed before every release | Pass | last executed on DL Release 2.1 [Sprint 20]
| Regression test scripts associated & executed as part of regression testing activity | Fail | Regression Story: SCDVR-5210 a. Test scripts are not attached to the story so unable to understand the regression testing scope as scripts are continuously modified at the end of each sprint b. Unable to review the testing outcomes
| Test data and/or screenshots captured for each script/ticket | Fail | No test documentations attached to confirm successful completion of regression testing.
| Detailed documentation of tickets - Problem Statement - Steps of Replicate - Actual Result - Expected Result - Test Data - Screenshots - Business Impact tagged as per severity - Key information populated on the ticket (Logged By, Tester, US, Sprint, Project, Status) | Partially Met | 1. Bug Observation a. Steps to replicate should be clearly stated in points if they are more than 2 instead of writing a paragraph or a statement b. Mention the issue in detail instead of stating a generic statement e.g. "Transaction Receipt not populating all data." c. No test data/scenario to trace the bug to test script when bug is logged/closed
| Outcomes reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Pass | Reviewed by Aparna Mahanta

## Bronze - DMV NMVTIS
Test Scripts & Scenarios
Category | Metrics | Results | Recommendations | Score
Test Scripts | Atomic | Pass | Only Happy path flow is validated & it is documented logically in the test script.
| Clear objective | Fail | Giving few examples to help team understand what needs to be corrected: 1. Brand Inquiry - Help Desk - Request Screen: SCDVR-4547, Brand Inquiry - Help Desk - Response Screen: SCDVR-4554, In-State Title Transfer or Change Data - Help Desk - Response Screen: SCDVR-3606, NMVTIS Old SOT Notified of CSOT Error - API Response - Salesforce: SCDVR-5185, NMVTIS Old SOT Notified of Their Error - API Response - Salesforce: SCDVR-5169 a. Test Script Format: i. Accurate Test Title - It should not be a direct copy paste of the US Summary if that isn't complete ii. Sequence # are not correct though it doesn’t look like any step was missed - copy paste issue
| Prerequisites, Personas & Org/Portal details mentioned | Partially Met | Giving few examples to help team understand what needs to be corrected: 1. Brand Inquiry - Help Desk - Response Screen: SCDVR-4554 1a. Test Script Format: i. Pre-requisites missing 2. NMVTIS Old SOT Notified of CSOT Error - API Response - Salesforce: SCDVR-5185, NMVTIS Old SOT Notified of Their Error - API Response - Salesforce: SCDVR-5169 a. Test Script Format: i. Pre-requisites should be drafted accurately to avoid misinterpretations with multiple references to "mentioned data" or "mentioned fields" ii. Pre-req seems to be incorrect as per the scope of US - Title should be Active & then updated to Inactive as per the response
| Detailed & concise documentation | Pass | Drafted scripts are well written given many are INT scripts to be tested using POSTMAN.
| Traceability to requirements | Pass | Scripts are atomic & can be tracked back to the requirements mentioned in US AC.
| Coverage: +ve/-ve scenarios, boundary value testing | Fail | 1. Brand Inquiry - Help Desk - Request Screen: SCDVR-4547 a. Exhaustive test coverage is missing i. Cover scenarios like special characters, VIN followed by zeros 2. Brand Inquiry - Help Desk - Response Screen: SCDVR-4554 a. Exhaustive test coverage is missing i. Validate the layout as well: green tick, alignment of message, VIN#, available options, etc. ii. Incorrect VIN search iii. Amendment Load Data isn't verified iv. Not all design inputs are validated as per the test documentation v. Recommendation: We should have "false" with F in CAPS! 3. In-State Title Transfer or Change Data - Help Desk - Response Screen: SCDVR-3606 a. Exhaustive test coverage is missing i. Layout validation ii. Incorrect VIN search iii. Warning/exceptions iv. Data type for the editable fields v. Conditions when optional table will show up with data 4. NMVTIS Old SOT Notified of CSOT Error - API Response - Salesforce: SCDVR-5185, 11. NMVTIS Old SOT Notified of Their Error - API Response - Salesforce: SCDVR-5169 a. Exhaustive test coverage is missing i. No validation for successful & error response ii. No validation for errors & warning iii. No validation for conversion exceptions iv. No validation for checks mentioned in Notes
| Format (inline w/ GC standards) | Pass | Test script format doesn’t align with GC as DMV uses Jira instead of Tracker. Also, current format looks good.
| Scripts reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Fail | No review performed
Regression Suite | Updated till Sprint current-1 | Pass | Yes, Confirmed by Asset Lead.
| Reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Fail | No review performed
| Format Recommendation: Script test cases module wise instead of maintaining 1 big e2e script | Partially Met | 1. Regression Suite 1a. Test script format: 1i. Test Title needs to be detailed to cover the scope of testing ii. Pre-requisites aren't complete or clear iii. Sequence # are not correct though it doesn’t look like any step was missed - copy paste issue
| Coverage: All modules w/ +ve/-ve, functional, UI, integration, etc. scenarios | Fail | 1. Regression Suite a. Exhaustive test coverage is missing ai. Only happy path e2e flow is covered for all transactions ii. NM-06 test script is missing
Execution
Scope Testing | Test scripts executed for each passed story | Fail | No test scripts for below mentioned user stories. 1. NMVTIS Old SOT Notified of CSOT Error - API Response - AAMVA to MuleSoft: SCDVR-5181 a. No test scripts present - If the US has no QA scope then it should be highlighted 2. NMVTIS Old SOT Notified of CSOT Error - API Response - MuleSoft to Salesforce: SCDVR-5183 a. No test scripts present - If the US has no QA scope then it should be highlighted 3. NMVTIS Old SOT Notified of Their Error - API Response - AAMVA to MuleSoft: SCDVR-5165 a. No test scripts present - If the US has no QA scope then it should be highlighted 4. NMVTIS Old SOT Notified of Their Error - API Response - MuleSoft to Salesforce: SCDVR-5167 a. No test scripts present - If the US has no QA scope then it should be highlighted 5. NMVTIS ¦ NM06 ¦ CSOT - Solicited - Response - AAMVA-> MF: SCDVR-5156 a. No test scripts present - If the US has no QA scope then it should be highlighted 6. NMVTIS ¦ NM06 ¦ CSOT - Solicited - Response - MF->SF: SCDVR-5158 a. No test scripts present - If the US has no QA scope then it should be highlighted
| Scope testing inline with test scripts | Pass | What is documented in test scripts is validated. Refer recommendation to make test scripts more exhaustive.
| Test data and/or screenshots captured for each user story/ticket | Fail | No test documentation for below mentioned user stories. 1. NMVTIS Old SOT Notified of CSOT Error - API Response - AAMVA to MuleSoft: SCDVR-5181 a. Attached response from AAMVA response doesn't align with the US AC - looks like a dummy response structure 2. NMVTIS Old SOT Notified of CSOT Error - API Response - MuleSoft to Salesforce: SCDVR-5183 a. Test documentation is missing & the UT document doesn’t cover SIT 3. NMVTIS Old SOT Notified of Their Error - API Response - AAMVA to MuleSoft: SCDVR-5165 a. Test documentation is missing & the UT document doesn’t cover SIT 4. NMVTIS Old SOT Notified of Their Error - API Response - MuleSoft to Salesforce: SCDVR-5167 a. Test documentation is missing & the UT document doesn’t cover SIT 5. NMVTIS ¦ NM06 ¦ CSOT - Solicited - Response - AAMVA-> MF: SCDVR-5156 a. Test documentation is missing & the UT document doesn’t cover SIT 6. NMVTIS ¦ NM06 ¦ CSOT - Solicited - Response - MF->SF: SCDVR-5158 a. Test documentation is missing & the UT document doesn’t cover SIT
| Detailed documentation of tickets - Problem Statement - Steps of Replicate - Actual Result - Expected Result - Test Data - Screenshots - Business Impact tagged as per severity - Key information populated on the ticket (Logged By, Tester, US, Sprint, Project, Status) | Partially Met | 1. Bug Observation: a. Issue Description should be documented clearly b. Steps to replicate should be clearly stated in points. c. No unresolved bugs should be present for a passed US
| Outcomes reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Fail | No review performed
Regression Testing | Regression suite executed before every release | Pass | Last executed on DL Release 1.1 [Sprint 9]
| Regression test scripts associated & executed as part of regression testing activity | Pass | Test scripts are attached to the scoped US. Recommendation: Regression testing scope should be called out in the story so the scope can be traced to the regression suite for coverage.
| Test data and/or screenshots captured for each script/ticket | Fail | Test documentation is missing
| Detailed documentation of tickets - Problem Statement - Steps of Replicate - Actual Result - Expected Result - Test Data - Screenshots - Business Impact tagged as per severity - Key information populated on the ticket (Logged By, Tester, US, Sprint, Project, Status) | Pass | Surprised to notice no bugs identified as part of regression testing!
| Outcomes reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Fail | No review performed

## Bronze - Kreator
Test Scripts & Scenarios
Category | Metrics | Results | Recommendations | Score
Test Scripts | Atomic | Fail | User Stories are atomic based on review however, this can only be confirmed once details are accurately added in the US.
| Clear objective | Partially Met | Giving few examples to help team understand what needs to be corrected: i. Test Description ambiguous 1. TS-008901 - TS-008903: 1) US AC says Text/picklist element but test script says button 2) Test Title to be clear in terms of testing scope. I believe we're testing search on text, picklist followed by both in these 3 scripts. 2. Test Description overall needs to be descriptive. It looks like same for multiple test scripts of the same US with minor difference which doesn’t really acts as a differentiator. 3. TS-008907: This verifies testing search for page variable of type object but it only adds up when US AC is mapped explicitly with test script steps ii. Expected Result is a copy paste of Introduction in majority of the scripts.
| Prerequisites, Personas & Org/Portal details mentioned | Fail | Giving few examples to help team understand what needs to be corrected: i. Test Script Format: 1. TS-008470, TS-008471, TS-008472: Pre-requisites missing for all MFA scripts 2. US-15876: Pre-req is missing for majority of test scripts. Simple pre-req applicable for multiple US's is user login, org details, existing data setup etc. 3. What should be added in pre-req is added as 1st step: TS-008922. Rather test script should start from validating the page in the SF.
| Detailed & concise documentation | Fail | Giving few examples to help team understand what needs to be corrected: i. Test scripts need to be meticulous Form Based Search US 1. It is observed that steps include steps like 'configure search criteria', 'add screen object', 'configure data table', etc. If these are new steps then they need to be detailed, else if they're existing flows then we should be good. Tip: It's good to always give a link of generic script in tips to help people w/o any prior hands-on experience with the tool understand the flow. 2. Missing steps- e.g. TS-008922 3. Unable to follow the steps as they are high-level - e.g. TS-008927 MFA US 1. Test steps need to be clear. For e.g., email template verification isn't accurate, error message which needs to be displayed 2. Write atomic steps instead of covering navigation, action & validation in single steps. E.g., TS-008470, TS-008471 3. TS-008477: Test scripts steps could have been framed better to confirm what action is being perform vs what is expected. Currently Action & Expected Result for many test steps don't align. For e.g., Validate if user has to refresh the tabs to see if they are logged out of all the duplicate tabs or automatically gets logged out this could be written as Validate when user explicitly refreshes the browser tabs, they're logged out of all the duplicate tabs.
| Traceability to requirements | Fail | User Stories lack detail & are mostly skeleton stories. Unable to trace to requirements to the stories even though scripts seem atomic.
| Coverage: +ve/-ve scenarios, boundary value testing | Fail | Giving few examples to help team understand what needs to be corrected: i. Exhaustive test coverage is missing Form Based Search US 1. There is no step to validate the checkbox 'Used for Search?' [Test the AC explicitly] 2. No mention for the note added on the Properties fields for Search checkbox but mentioned in test script 3. No scripts to test Query Framework Modal 4. Search Configuration: 1) No negative tests around incorrect page variable mapping 5. No script to test flow for Screen object w/o search functionality for Text & picklist elements 6. All permutations & combinations not covered as per AC - e.g. Text Element AC# 3,4 & Picklist Element AC# 3-6 MFA US 1. TS-008469: No check for email received, no check for UI when login with SSO button is clicked 2. Cross browser testing on Firefox, Chrome & Safari 3. Session expiry & logout validation in different windows & incognito sessions of same browser & different browsers API Metadata via Swagger 1. Check to insert duplicate field data 2. How about delete scenario
| Format (inline w/ GC standards) | Pass | Tip: When doing cut/copy/paste of test steps, please ensure to have the test steps in sequence. [US-15876]
| Scripts reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Pass | Reviewed by Sai Charan
Regression Suite | Updated till Sprint current-1 | Pass | Yes, Confirmed by Asset QA Lead.
| Reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Pass | Reviewed by Sai Charan
Format Recommendation: Script test cases module wise instead of maintaining 1 big e2e script
Coverage: All modules w/ +ve/-ve, functional, UI, integration, etc. scenarios
Execution
Scope Testing | Test scripts executed for each passed story | Pass | Test scripts are attached to US with QA effort.
| Scope testing inline with test scripts | Pass | All documented scripts are executed.
| Test data and/or screenshots captured for each user story/ticket | Fail | No test execution document (Test data, screenshot, video) attached to majority of scripts. Also, none of the tickets have comments/screenshots while closing the ticket.
| Detailed documentation of tickets - Problem Statement - Steps of Replicate - Actual Result - Expected Result - Test Data - Screenshots - Business Impact tagged as per severity - Key information populated on the ticket (Logged By, Tester, US, Sprint, Project, Status) | Partially Met | i. There are open tickets even though US is passed. They should ideally be moved to next sprint/backlog ticket US. [US-15876] ii. Expected Result is not captured. Even though error snippet is added or error is mentioned as part of Problem Summary, its advised to mentioned the Expected & Actual result. iii. No comments/screenshots while closing the ticket iv. No traceability of ticket to test script when there are more than 1 test scripts
| Outcomes reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Pass | Reviewed by Sai Charan
Regression Testing | Regression suite executed before every release | Pass | Last executed on 3/13.
| Regression test scripts associated & executed as part of regression testing activity | Partially Met | i. No test scripts attached when scope is identified for the US: US-15912, US-15913, US-15916. Recommendation is to split the test cases as per the defined scope of the US instead of attached them to a parent story unless all are child stories. ii. 1 test script attached (which doesn't look cover entire scope or even scope carved out for regression test placeholder story) is not executed: US-15915
| Test data and/or screenshots captured for each script/ticket | Fail | No test execution document (Test data, screenshot, video) attached to majority of scripts. Also, none of the tickets have comments/screenshots while closing the ticket.
| Detailed documentation of tickets - Problem Statement - Steps of Replicate - Actual Result - Expected Result - Test Data - Screenshots - Business Impact tagged as per severity - Key information populated on the ticket (Logged By, Tester, US, Sprint, Project, Status) | Fail | Surprised to notice no bugs identified as part of regression testing! Marking this as Failed as it is not possible to run more than 100 scripts w/o identifying even a single bug.
| Outcomes reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Pass | Reviewed by Sai Charan

## Bronze - Core
Test Scripts & Scenarios
Category | Metrics | Results | Recommendations | Score
Test Scripts | Atomic | Fail | 1. Each Sequence step should have 1 Action step. 2. Test Scripts should be divided wrt +ve and -ve scenarios
| Clear objective | Pass
| Prerequisites, Personas & Org/Portal details mentioned | Partially Met | Details present for some of the US and not there for some.
| Detailed & concise documentation | Pass | Steps are clear. However, refer to 3rd row for atomic scripting
| Traceability to requirements | Pass
| Coverage: +ve/-ve scenarios, boundary value testing | Partially Met | positive and negative testing is covered for some and not covered for some. Also, separate TS have to be written for +ve & -ve scenarios instead of including both in a single TS
| Format (inline w/ GC standards) | Pass
| Scripts reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Pass
Regression Suite | Updated till Sprint current-1 | Fail | The TS in the GC-QA Regression folder has latest update date in Sept 2022
| Reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Pass
| Format Recommendation: Script test cases module wise instead of maintaining 1 big e2e script | Pass | Scripts are module-wise
| Coverage: All modules w/ +ve/-ve, functional, UI, integration, etc. scenarios | Partially Met | Only +ve scenarios covered
Execution
Scope Testing | Test scripts executed for each passed story | Pass | Test Scripts are uploaded to the US. However, they have to be atomic
| Scope testing inline with test scripts | Pass
| Test data and/or screenshots captured for each user story/ticket | Partially Met | Screenshots are not captured for some of the US. Also its recommended to attach the screenshots separately for each TS instead of uploading all together to the US.
| Detailed documentation of tickets - Problem Statement - Steps of Replicate - Actual Result - Expected Result - Test Data - Screenshots - Business Impact tagged as per severity - Key information populated on the ticket (Logged By, Tester, US, Sprint, Project, Status) | Fail | Screenshots are not present for any TKT related to the provided US.
| Outcomes reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Pass | Reviewed by Sunil and Zafar
Regression Testing | Regression suite executed before every release | Partially Met | Not exactly the Regression suit. But performed End-to-End testing as informed by Sunil.
| Regression test scripts associated & executed as part of regression testing activity | Fail | Test Scripts are not uploaded to the Regression User Story. However, they are placed in the GoveCOnnect Regression folder on Teams
| Test data and/or screenshots captured for each script/ticket | Fail | Test Scripts are not uploaded to the Regression User Story. Hence cannot validate the Test data and Screenshots
| Detailed documentation of tickets - Problem Statement - Steps of Replicate - Actual Result - Expected Result - Test Data - Screenshots - Business Impact tagged as per severity - Key information populated on the ticket (Logged By, Tester, US, Sprint, Project, Status) |  | There are no TKTs raised as part of regression testing. (no TKTs tagged to the US)
| Outcomes reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Pass | Reviewed by Sunil and Zafar

## Bronze - CS
Test Scripts & Scenarios
Category | Metrics | Results | Recommendations | Score
Test Scripts | Atomic | Fail | No TS in the User Stories provided
| Clear objective | Fail | No TS in the User Stories provided
| Prerequisites, Personas & Org/Portal details mentioned | Fail | No TS in the User Stories provided
| Detailed & concise documentation | Fail | No TS in the User Stories provided
| Traceability to requirements | Fail | AC is generic like perform E2E validation of Employee portal / SSP. Couldn’t validate traceability
| Coverage: +ve/-ve scenarios, boundary value testing | Fail | No TS in the User Stories provided
| Format (inline w/ GC standards) | Fail | No TS in the User Stories provided
| Scripts reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Fail | No TS drafted for Lead to review
Regression Suite | Updated till Sprint current-1 | Fail | The TS in the GC-QA Regression folder has latest update date in Sept 2022
| Reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Pass | As informed by Amol in the email
| Format Recommendation: Script test cases module wise instead of maintaining 1 big e2e script | Pass
| Coverage: All modules w/ +ve/-ve, functional, UI, integration, etc. scenarios | Partially Met | Positive scenarios covered
Execution
Scope Testing | Test scripts executed for each passed story | Fail | No TS in the User Stories provided
| Scope testing inline with test scripts | Fail | No AC defined & No TS are uploaded to the US
| Test data and/or screenshots captured for each user story/ticket | Partially Met | Screenshots captured for few US and not captured for few. Also its recommended to attach the screenshots separately for each TS instead of uploading all together to the US.
| Detailed documentation of tickets - Problem Statement - Steps of Replicate - Actual Result - Expected Result - Test Data - Screenshots - Business Impact tagged as per severity - Key information populated on the ticket (Logged By, Tester, US, Sprint, Project, Status) | Partially Met | 1. Steps to reproduce are not there for all the TKTs. Some of them only have the issue description. 2. Only expected result is mentioned for all the TKTs. Issue / Actual result should be added
| Outcomes reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Pass | As informed by Amol in the email
Regression Testing | Regression suite executed before every release | Pass | As informed by Amol in the email
| Regression test scripts associated & executed as part of regression testing activity | Fail | Regression TS in the US provided and the TS in Suite are different
| Test data and/or screenshots captured for each script/ticket | Fail | There is no Test Execution for the TS. No Screenshots
| Detailed documentation of tickets - Problem Statement - Steps of Replicate - Actual Result - Expected Result - Test Data - Screenshots - Business Impact tagged as per severity - Key information populated on the ticket (Logged By, Tester, US, Sprint, Project, Status) |  | There are no TKTs raised as part of regression testing. (no TKTs tagged to the US)
| Outcomes reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Pass | As informed by Amol in the email

## Bronze - LTSS
Test Scripts & Scenarios
Category | Metrics | Results | Recommendations | Score
Test Scripts | Atomic | Partially Met | TS are atomic but not detailed.
| Clear objective | Pass
| Prerequisites, Personas & Org/Portal details mentioned | Partially Met | Details present for some of the US and not there for some.
| Detailed & concise documentation | Fail | Most of the TS seemed like Unit Test Scripts
| Traceability to requirements | Partially Met | Some US doesn’t have TS written. For the ones, written, able to trace. However, the TS are not detailed
| Coverage: +ve/-ve scenarios, boundary value testing | Fail | Only +ve scenarios covered. All the US provided are implementing a small functionality. There are no integration US.
| Format (inline w/ GC standards) | Partially Met
| Scripts reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Pass
Regression Suite | Updated till Sprint current-1 | Pass
| Reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Pass
| Format Recommendation: Script test cases module wise instead of maintaining 1 big e2e script | Pass
| Coverage: All modules w/ +ve/-ve, functional, UI, integration, etc. scenarios | Partially Met | Only +ve scenarios covered
Execution
Scope Testing | Test scripts executed for each passed story | Partially Met | Some US doesn’t have TS.
| Scope testing inline with test scripts | Pass
| Test data and/or screenshots captured for each user story/ticket | Pass | Its recommended to add Screenshots to the Test Scripts instead of US. Few TKTs doesn’t have Issue SS
| Detailed documentation of tickets - Problem Statement - Steps of Replicate - Actual Result - Expected Result - Test Data - Screenshots - Business Impact tagged as per severity - Key information populated on the ticket (Logged By, Tester, US, Sprint, Project, Status) | Fail | Most of the TKTs doesn’t have Steps to reproduce, Actual & Expected results, Clear Issue description and TKT Closing comments
| Outcomes reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Pass
Regression Testing | Regression suite executed before every release | Pass | As informed by Preeti on email
| Regression test scripts associated & executed as part of regression testing activity | Partially Met | TS are uploaded to only 1 US out of 3 US provided
| Test data and/or screenshots captured for each script/ticket | Fail | No screenshots attached to US / TKT
| Detailed documentation of tickets - Problem Statement - Steps of Replicate - Actual Result - Expected Result - Test Data - Screenshots - Business Impact tagged as per severity - Key information populated on the ticket (Logged By, Tester, US, Sprint, Project, Status) | Fail | 1 TKT raised as part of regression. It doesn’t have any details
| Outcomes reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Pass

## Bronze- CW
Test Scripts & Scenarios
Category | Metrics | Results | Recommendations | Score
Test Scripts | Atomic | Fail | - No script/ test validation document is added in the story. Video recording is added for two stories but that is not how we should close a story. Example:US-14600, US-13370, US-13628
| Clear objective | Fail | No test script present for the mentioned story
| Prerequisites, Personas & Org/Portal details mentioned | Fail | No test script present for the mentioned story
| Detailed & concise documentation | Fail | No test script present for the mentioned story
| Traceability to requirements | Fail | No test script present for the mentioned story
| Coverage: +ve/-ve scenarios, boundary value testing | Fail | No test script present for the mentioned story
| Format (inline w/ GC standards) | Fail | No test script present for the mentioned story
| Scripts reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Fail | No test script present for the mentioned story
Regression Suite | Updated till Sprint current-1 | Fail | Updated till sprint 61
| Reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Pass | Reviewed by Venumadhav Samala
| Format Recommendation: Script test cases module wise instead of maintaining 1 big e2e script | Partially Met | Passed: - Regression scripts are created module wise. - Details are mentioned specifically - User personas are mentioned Failed: - Only positive scenario is scripted. (Example- IL Case, Intake Module, Permanency guardianship case, Permenancy Adoption case ) - Pre requisite not mentioned. (Example- Intake Module) -Test Titles are not clear. (Example- Intake Module, Investigation Case Module, Permenancy Adoption case ) - No Test title, Pre-requisite, summary are mentioned( Example- Provider Portal regression suite, Reporter Portal regression Suite)
| Coverage: All modules w/ +ve/-ve, functional, UI, integration, etc. scenarios | Fail | Negative scenarios are not mentioned in the regression suite.
Execution
Scope Testing | Test scripts executed for each passed story | Fail | No script is added with the story
| Scope testing inline with test scripts | Fail | No script is added with the story
| Test data and/or screenshots captured for each user story/ticket | Partially Met | Screenshot is captured only for the tickets (after fix)
| Detailed documentation of tickets - Problem Statement - Steps of Replicate - Actual Result - Expected Result - Test Data - Screenshots - Business Impact tagged as per severity - Key information populated on the ticket (Logged By, Tester, US, Sprint, Project, Status) | Partially Met | - Screenshot for the defect is not present. - Business impact is mostly selected as HIgh for most of the tickets where as some of the ticket's priority should be different. TKT-011435 should be a critical ticket instead of a high priority. - Problem summary should be specific to the issue. for below mentioned tickets, problem summaryis not accurate. TKT- 011962, TKT-011960 - No qa scope is tracked as part of US- 16972 - Module name/ Screen Name is not mentioned for most of the tickets
| Outcomes reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Fail | No outcomes are attached with the user stories.
Regression Testing | Regression suite executed before every release | Pass | Confirmed by the Asset lead
| Regression test scripts associated & executed as part of regression testing activity | Fail | Regression test Script and test validation are not attached with the story (US-16166, US-16987)
| Test data and/or screenshots captured for each script/ticket | Partially Met | Screenshot of the defect is not attached but Scrrenshot after the fix is attached with the ticket(TKT-013403, TKT-013405, ) .
| Detailed documentation of tickets - Problem Statement - Steps of Replicate - Actual Result - Expected Result - Test Data - Screenshots - Business Impact tagged as per severity - Key information populated on the ticket (Logged By, Tester, US, Sprint, Project, Status) | Partially Met | Screenshot of the defect is not attached but Scrrenshot after the fix is attached with the ticket(TKT-013403, TKT-013405, ) .
| Outcomes reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Fail | No outcome/ validation document present in the regression stories.

## Bronze- Grants
Test Scripts & Scenarios
Category | Metrics | Results | Recommendations | Score
Test Scripts | Atomic | Pass | 1- No test script and test validation document attached with the story. (US- 13861, US-14467, US-13413, US-13414,US-13417 ,US-13420, US-13418) 2- Test Scripts are atomic.
| Clear objective | Pass | For the stories, where the test scripts are uploaded, objectives are clear.
| Prerequisites, Personas & Org/Portal details mentioned | Fail | 1- Pre-requisite not mentioned (US- 13819, US-13833, US-13935, US-14037, US-13412, US-14350, TS-009437, TS-009439, TS-009458, TS-009459, TS-009395, TS-009396, TS-009441, TS-009445, TS-007775) 2- User personas are not mentioned in the test scripts. (US-13819, US- 13832, US-13833, US-13935, US-14037,US-13412, TS-007775)
| Detailed & concise documentation | Partially Met | 1- No test validation document attached with the story in ASG tracker but test execution was completed. (US- 13819, US-13833,US-14037,). 2- No test validation document attached with the story in ASG tracker (US-14467,US-13412 , US-13413, US-13414, US-13417, US-13420, US-14350 3- Test Execution task not completed in ASG Tracker: US-17147
| Traceability to requirements | Pass | Scripts are atomic & can be tracked back to the requirements mentioned in US AC.
| Coverage: +ve/-ve scenarios, boundary value testing | Partially Met | 1- Negative and postive scenarios are mentioned under one script. (US-13891, US- 13832, US-13935, ) 2- Negative scenarios are not mentioned. Only postive scenario are covered. (US-17149, US-17153 3- test data details are not present in the test scripts like, what type of value need to be provided.
| Format (inline w/ GC standards) | Pass
| Scripts reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Pass
Regression Suite | Updated till Sprint current-1 | Pass
| Reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Pass | Reviewed by Rakesh
| Format Recommendation: Script test cases module wise instead of maintaining 1 big e2e script | Partially Met | 1-Negative scenario is not mentioned for Application, Sources, validate module 2-Pre-requisite details are not mentioned 3-user personas are not mentioned for Sources module 4-No test Title and scenario are mentioned for Financial module, Evaluation Module, review questionnaire, budget, rewards.
| Coverage: All modules w/ +ve/-ve, functional, UI, integration, etc. scenarios | Partially Met | Positive, functional scenarios are covered as part of regression suite.
Execution
Scope Testing | Test scripts executed for each passed story | Fail | 1- No test script and test validation document attached with the story. (US- 13861, US-14467, US-13413, US-13414,US-13417 ,US-13420, US-13418, US-13421, US-13422, US-14465, US-14469, US-14470,US-14466, US-14351, US-14355,US-14378,US-14384, ) 2- No test validation document attached with the story in ASG tracker (US-14467,US-13412 , US-13413, US-13414, US-13417, US-13420, US-14350, TS-009458) 3- Test Execution task wasn't completed but validation document are present.( US-17150, US-17152
| Scope testing inline with test scripts | Pass
| Test data and/or screenshots captured for each user story/ticket | Partially Met | 3- Test Validation screenshot after the defects are fixed, not attached with the ticket. (TKT-012222, TKT-012228, TKT-012524, TKT-012503, TKT-013779, TKT-010420, 4- No screenshot of the ticket is present.(TKT-012228, TKT-012524
| Detailed documentation of tickets - Problem Statement - Steps of Replicate - Actual Result - Expected Result - Test Data - Screenshots - Business Impact tagged as per severity - Key information populated on the ticket (Logged By, Tester, US, Sprint, Project, Status) | Fail | 1- Expected result is not mentioned for the tickets. (TKT-012222, TKT-012228, TKT-012524, TKT-012503, TKT-012524, TKT-009040, TKT-009043, TKT-009003, TKT-009022, TKT-009064 2- Steps to re-produce the tickets are not mentioned. (TKT-012222, TKT-012228, TKT-012524, TKT-012503, TKT-012954, TKT-012583, TKT-009040, TKT-009043, TKT-009003) 3- Test Validation screenshot after the defects are fixed, not attached with the ticket. (TKT-012222, TKT-012228, TKT-012524, TKT-012503, TKT-013739 4- No screenshot of the ticket is present.(TKT-012228, TKT-012524, TKT-009040, TKT-009043, TKT-009003 5- Problem description is not mentioned properly with no details. No screenshot present and no expected results are mentioned.(TKT-010420, TKT-008953, TKT-008954, TKT-008955, TKT-008957, TKT-008958,TKT-008960, TKT-009064
| Outcomes reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Pass
Regression Testing | Regression suite executed before every release | Fail | Team has started doing this from Sprint 29
| Regression test scripts associated & executed as part of regression testing activity | Fail | No User story were created and QA activities were not scoped
| Test data and/or screenshots captured for each script/ticket | Fail | No User story were created and QA activities were not scoped
| Detailed documentation of tickets - Problem Statement - Steps of Replicate - Actual Result - Expected Result - Test Data - Screenshots - Business Impact tagged as per severity - Key information populated on the ticket (Logged By, Tester, US, Sprint, Project, Status) | Fail | No User story were created and QA activities were not scoped
| Outcomes reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Fail | No User story were created and QA activities were not scoped

## Bronze - IDS
Test Scripts & Scenarios
Category | Metrics | Results | Recommendations | Score
Test Scripts | Atomic | Pass | For the stories where the test script is attached, steps are atomic based on the requirements.
| Clear objective | Pass | Test Title, Introduction, Expected results can not be the same.(TS-008244, TS-008241
| Prerequisites, Personas & Org/Portal details mentioned | Partially Met | No pre-requisite mentioned for the script (TS-008244, TS-008241, TS-008289, TS-008290, TS-008291, TS-008292,TS-008245, TS-008246, TS-008309, TS-008310 User personas and org details are mentioned
| Detailed & concise documentation | Partially Met | No test validation document present(US-15073, Detailed information on patient creation is not mentioned. (TS-008245,
| Traceability to requirements | Pass | as per requirement, details are mentioned.
| Coverage: +ve/-ve scenarios, boundary value testing | Partially Met | Only positive scenario is mentioned. No negative scenario covered as part of the test script(US-15743, US-15073
| Format (inline w/ GC standards) | Pass
| Scripts reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Pass | Reviewed by Ankur Verma
Regression Suite | Updated till Sprint current-1 | Pass | Confirmed by the asset lead
| Reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Pass | Reviewed by Ankur Verma
| Format Recommendation: Script test cases module wise instead of maintaining 1 big e2e script | Pass | 1- Specific details are mentioned with user personas. 2- Pre-requisite is not mentioned for the Review DR flow. (US-16634)
| Coverage: All modules w/ +ve/-ve, functional, UI, integration, etc. scenarios | Fail | 1- Negative scearios are not mentioned for the disease report flow.(example: there should be a negative scenario mentioning all the required details in case user do not provide. in that case- a DR can not be created.) 2- exhaustive test details are not mentioned. it is mentioned required details need to be provided but which are the required fields, that is not mentioned in any step. 3- Details of outbreak details are not mentioned as in which all details will be shown while trying to delink the outbreak from an investigation. (investigation manage outbreak) 4- color of the alert symbol should be mentioned in the script for better user experience. (Create Outbreak) 5- Required test data details/field details are not mentioned and which all details will be present under the related list are not mentioned(Create exposed contacts)
Execution
Scope Testing | Test scripts executed for each passed story | Fail | 1- No test script and test validation document attached on the story(US-15123, US-15067, US-15467, US-14987, US-14956, US-15132 2- If QA is not required, that need to be mentioned in the story (US-15067, US-15467 3- No test validation document attached in the story: US-15074, US-15073, US-15127, US-14955, US-15090) 4- No test script added but test validation documents are present : US-14983
| Scope testing inline with test scripts | Pass
| Test data and/or screenshots captured for each user story/ticket | Partially Met | 1- No test script and test validation document attached on the story(US-15123, US-15067, US-15467 2- If QA is not required, that need to be mentioned in the story (US-15067, US-15467 3- No test validation document attached in the story: US-15074, US-15073, US-15127)
| Detailed documentation of tickets - Problem Statement - Steps of Replicate - Actual Result - Expected Result - Test Data - Screenshots - Business Impact tagged as per severity - Key information populated on the ticket (Logged By, Tester, US, Sprint, Project, Status) | Fail | 1- Portal details are not mentioned in the ticket: TKT-011992 2- No validation document attached once the ticket is fixed: TKT-012674 3- GC standards for creating a ticket is not followed(ex: observation, expectation). only one line description is present. (TKT-011104, TKT-012766, TKT-012900, TKT-012906, TKT-012912, TKT-013027)
| Outcomes reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Pass | Reviewed by Ankur Verma
Regression Testing | Regression suite executed before every release | Fail | 1- No test execution tasks were completed as part of US- US-15369 and US-15370. Only the Regression script is uploaded. No test validation document are uploaded in the story.
| Regression test scripts associated & executed as part of regression testing activity | Fail | 1-Test script is associated with the story but no test validation document is attached(US-15369 & US- 15370)
| Test data and/or screenshots captured for each script/ticket | Fail | No documents are attached.(US-15369 & US-15370)
| Detailed documentation of tickets - Problem Statement - Steps of Replicate - Actual Result - Expected Result - Test Data - Screenshots - Business Impact tagged as per severity - Key information populated on the ticket (Logged By, Tester, US, Sprint, Project, Status) | Fail | 1-No tickets are present(US-15369) 2- No ticket screenshot attached for the ticket only the screenshot after the ticket is fixed are attached. (TKT-012932, TKT-012894, TKT-012896, TKT-012895, TKT-012898, TKT-012899 3- GC standards for creating a ticket is not followed(ex: observation, expectation). only one line description is present. (TKT-012932, TKT-012894, TKT-012896, TKT-012895, TKT-012898, TKT-012899
| Outcomes reviewed by USI Asset Lead/QA Lead/Functional Lead (as applicable) | Fail | Reviewed by Ankur Verma but was unable to see the outcome validation attached in the story. (US-15369)